## Estimation Matrix
DESKTOP/CLIENT APPLICATION UPGRADE - ESTIMATION RUBRIC
Instructions: Select complexity level (1-5) for each attribute. Yellow cells are inputs. Effort hours auto-calculate based on Base Hours × Conversion Factor.
Category | Attribute | Description | Low (1) | Medium (3) | High (5) | Selection (1-5) | Base Hours (Industry Std) | Conversion Factor | Effort (Hrs) | Weighted Effort (Hrs)
Scope | Workstation Count | Number of workstations/endpoints | 1-25 workstations | 26-100 workstations | 101+ workstations | 1 | 4 | 0.33 | 1.3
| Application Type | Type of client application | Standalone tool | Client with server dependency | Thick client (heavy server integration) | 1 | 5 | 0.33 | 1.7
| User Population | Types of users affected | IT/technical users only | Single department | Multiple departments/enterprise-wide | 1 | 4 | 0.33 | 1.3
| Geographic Distribution | Location of workstations | Single site | Multiple sites, same timezone | Multiple sites, global distribution | 1 | 4 | 0.33 | 1.3
| Environment Coverage | Environments to upgrade | Production only | Test + Production | Dev + Test + UAT + Production | 1 | 3 | 0.33 | 1
Client-Server | Server Version Dependency | Client-server version coupling | Client version independent | Must match major version | Must match exact version | 1 | 8 | 0.33 | 2.6
| Protocol/API Compatibility | Communication protocol changes | No protocol changes | Minor protocol updates | Major protocol/API changes | 1 | 6 | 0.33 | 2
| Backward Compatibility | Old client support during rollout | Server supports old + new clients | Limited backward compatibility | No backward compatibility (big bang) | 1 | 8 | 0.33 | 2.6
| Connection String/Config | Server connection configuration | No config changes | Minor config updates | Major connection reconfiguration | 1 | 4 | 0.33 | 1.3
| Authentication Changes | Auth mechanism changes | No auth changes | Token/credential refresh | New auth method (SSO, MFA) | 1 | 6 | 0.33 | 2
Client Application | Version Jump | Gap between current and target | Minor version (N.x to N.y) | Major version (N to N+1) | Multi-major jump (N to N+2+) | 1 | 8 | 0.33 | 2.6
| Installation Complexity | Install/upgrade process | Silent install, no interaction | Some user interaction needed | Complex multi-step installation | 1 | 6 | 0.33 | 2
| Local Data Migration | User data/settings migration | Auto-migrated by installer | Manual export/import needed | Complex data transformation | 1 | 6 | 0.33 | 2
| User Profile Impact | Windows profile/AppData changes | No profile impact | Settings reset/reconfiguration | Profile rebuild required | 1 | 4 | 0.33 | 1.3
| Prerequisite Changes | Runtime/.NET/Java requirements | Same prerequisites | Minor updates (auto-install) | Major new prerequisites | 1 | 6 | 0.33 | 2
Deployment Target | Deployment Target Complexity | Uniformity of target environment | Single target type (all VDI or all physical, uniform) | Mixed (VDI + physical, or 2-3 configs) | Highly diverse (multiple VDI pools + physical + varied configs) | 1 | 6 | 0.33 | 2
| Hardware Compatibility | Do existing targets meet requirements | All targets meet requirements | 80-95% meet requirements, exceptions manageable | <80% meet requirements, blocked until resolved | 1 | 4 | 0.33 | 1.3
| OS Compatibility | Windows/OS version support | All current OS supported | Some OS versions need updates | OS upgrade required first | 1 | 6 | 0.33 | 2
| VDI Image Management | Golden image updates (N/A=1 for physical) | N/A or single image update | 2-3 image variants to update | 4+ image variants or complex layering | 1 | 4 | 0.33 | 1.3
Deployment | Deployment Method | How clients will be deployed | SCCM/Intune automated | GPO/scripted deployment | Manual installation | 1 | 6 | 0.33 | 2
| Deployment Waves | Rollout approach | Single wave (all at once) | 2-3 waves (pilot → production) | 4+ waves (gradual rollout) | 1 | 4 | 0.33 | 1.3
| User Downtime | User impact during install | Background install, no downtime | Brief downtime (< 30 min) | Extended downtime (> 30 min) | 1 | 4 | 0.33 | 1.3
| Self-Service Option | User-initiated install available | Fully self-service | IT-assisted self-service | IT must perform install | 1 | 3 | 0.33 | 1
| Uninstall Old Version | Old version removal | Auto-uninstall by new installer | Separate uninstall step | Manual cleanup required | 1 | 4 | 0.33 | 1.3
Licensing | License Model Change | Licensing changes | Same license model | License key/activation update | New license model (subscription, etc.) | 1 | 4 | 0.33 | 1.3
| License Count | License availability | Sufficient licenses | Need true-up/additional | Major license procurement | 1 | 3 | 0.33 | 1
| License Server Impact | License server changes | No license server | License server update needed | New license server required | 1 | 4 | 0.33 | 1.3
Testing | Test Environment | Client test environment | Dedicated test workstations/VDI | Limited test environment | No test environment (prod pilot) | 1 | 4 | 0.33 | 1.3
| Functional Testing | Application functionality testing | Smoke test sufficient | Key workflow validation | Full regression testing | 1 | 8 | 0.33 | 2.6
| Server Integration Testing | Client-server integration tests | Basic connectivity test | Transaction/workflow testing | Full end-to-end testing | 1 | 6 | 0.33 | 2
| User Acceptance Testing | UAT scope | IT validation only | Power user UAT | Business-wide UAT | 1 | 6 | 0.33 | 2
Change Mgmt | Change Approval Process | CAB/approval overhead | Pre-approved standard change | Normal change (CAB review) | Emergency/expedited change | 1 | 2 | 0.33 | 0.7
| User Communication | End-user notification | Email notification | Training documentation | Hands-on training required | 1 | 4 | 0.33 | 1.3
| Help Desk Preparation | Support team readiness | Minor FAQ update | Help desk training needed | Dedicated support during rollout | 1 | 3 | 0.33 | 1
| Stakeholder Coordination | Teams to coordinate | 1-2 teams | 3-5 teams | 6+ teams / external parties | 1 | 3 | 0.33 | 1
Risk | Rollback Capability | Ability to revert to old client | Side-by-side or VDI image revert | Uninstall/reinstall old version | No rollback possible | 1 | 4 | 0.33 | 1.3
| Business Criticality | Application importance | Convenience tool | Business important | Mission critical | 1 | 4 | 0.33 | 1.3
| Rollout Timeline | Deadline pressure | Flexible (> 30 days) | Standard (14-30 days) | Urgent (< 14 days) | 1 | 3 | 0.33 | 1
ESTIMATION SUMMARY
Total Base Hours (reference): | [6 empty] | 181
Total Estimated Effort (Hours): | [8 empty] | 59.6
Contingency % (input): | [5 empty] | 15% |  |  | 8.94
Total with Contingency (Hours): | [8 empty] | 68.54
Estimated Days (8 hr/day): | [8 empty] | 8.6

## Project Type Presets
DESKTOP/CLIENT APPLICATION UPGRADE - PROJECT TYPE PRESETS
Heavy Manufacturing Enterprise. Green=Low (1-2), Yellow=Medium (3), Red=High (4-5). Use as starting point.
Category | Attribute | ERP Client | PLM/PDM Client | CAD/CAM Client | MES/Shop Floor Client | Quality/ Compliance | Admin/IT Tools
Scope | Workstation Count | 5 | 3 | 3 | 4 | 3 | 1
| Application Type | 5 | 5 | 4 | 5 | 4 | 2
| User Population | 5 | 3 | 2 | 4 | 3 | 1
| Geographic Distribution | 4 | 3 | 2 | 3 | 2 | 2
| Environment Coverage | 4 | 3 | 2 | 3 | 3 | 2
Client-Server | Server Version Dependency | 5 | 5 | 4 | 5 | 4 | 2
| Protocol/API Compatibility | 3 | 4 | 3 | 4 | 3 | 1
| Backward Compatibility | 3 | 2 | 2 | 2 | 3 | 4
| Connection String/Config | 3 | 3 | 2 | 4 | 2 | 1
| Authentication Changes | 3 | 3 | 2 | 3 | 3 | 2
Client Application | Version Jump | 3 | 4 | 3 | 3 | 3 | 2
| Installation Complexity | 3 | 4 | 4 | 3 | 3 | 1
| Local Data Migration | 2 | 4 | 4 | 2 | 3 | 1
| User Profile Impact | 3 | 3 | 4 | 2 | 2 | 1
| Prerequisite Changes | 3 | 4 | 4 | 3 | 3 | 2
Deployment Target | Deployment Target Complexity | 3 | 3 | 4 | 4 | 2 | 1
| Hardware Compatibility | 2 | 3 | 4 | 3 | 2 | 1
| OS Compatibility | 2 | 3 | 3 | 3 | 2 | 2
| VDI Image Management | 3 | 3 | 4 | 2 | 2 | 1
Deployment | Deployment Method | 2 | 3 | 4 | 3 | 3 | 2
| Deployment Waves | 5 | 3 | 3 | 4 | 3 | 1
| User Downtime | 2 | 3 | 4 | 5 | 2 | 1
| Self-Service Option | 4 | 4 | 4 | 5 | 3 | 2
| Uninstall Old Version | 2 | 3 | 3 | 2 | 2 | 1
Licensing | License Model Change | 2 | 2 | 2 | 2 | 2 | 1
| License Count | 3 | 3 | 3 | 2 | 2 | 1
| License Server Impact | 2 | 4 | 4 | 2 | 2 | 1
Testing | Test Environment | 3 | 3 | 3 | 4 | 3 | 2
| Functional Testing | 5 | 5 | 4 | 5 | 4 | 2
| Server Integration Testing | 5 | 5 | 3 | 5 | 4 | 2
| User Acceptance Testing | 5 | 4 | 4 | 4 | 4 | 1
Change Mgmt | Change Approval Process | 3 | 3 | 2 | 4 | 4 | 1
| User Communication | 5 | 4 | 3 | 4 | 3 | 1
| Help Desk Preparation | 4 | 3 | 3 | 4 | 3 | 1
| Stakeholder Coordination | 5 | 4 | 3 | 5 | 3 | 1
Risk | Rollback Capability | 2 | 3 | 3 | 4 | 2 | 1
| Business Criticality | 5 | 5 | 4 | 5 | 4 | 2
| Rollout Timeline | 3 | 3 | 3 | 4 | 3 | 2

## Effort Breakdown
DETAILED EFFORT BREAKDOWN BY PHASE
|  |  | Total Hours (from Matrix): | 100
Phase | Task Category | Typical % | Est. Hours | Notes
1. Planning | Compatibility assessment | 5% | 5
| Server dependency analysis | 4% | 4
| Target environment audit | 4% | 4
| Deployment strategy | 3% | 3
| Change request submission | 2% | 2
2. Preparation | Package creation/testing | 8% | 8
| License procurement/activation | 3% | 3
| Test environment validation | 6% | 6
| VDI image preparation | 4% | 4
| User communication | 3% | 3
| Help desk training | 3% | 3
3. Pilot | Pilot group deployment | 6% | 6
| Pilot user validation | 4% | 4
| Issue resolution | 4% | 4
4. Deployment | Wave 1 deployment | 8% | 8
| Wave 2+ deployment | 8% | 8
| Failed install remediation | 4% | 4
| User support during rollout | 6% | 6
5. Validation | Server integration testing | 4% | 4
| Functional spot checks | 3% | 3
| Performance validation | 2% | 2
6. Closure | Old version cleanup | 3% | 3
| Documentation updates | 2% | 2
| Lessons learned | 1% | 1
| TOTAL | 100% | 100

## Documentation
DESKTOP/CLIENT APPLICATION UPGRADE ESTIMATION RUBRIC
Documentation & User Guide
OVERVIEW
Purpose: | Standardized estimation for desktop/client application upgrades including server-dependent thick clients.
Coverage: | ~90% of client application upgrade scenarios in heavy manufacturing.
In Scope: | ERP clients, PLM/PDM clients, CAD/CAM tools, MES/Shop Floor clients, Quality/Compliance tools.
Out of Scope: | Hardware installation/upgrades (separate project), pure web apps, mobile apps.
CATEGORIES EXPLAINED
Scope | Basic sizing: workstation count, application type, user population, geographic distribution.
Client-Server | Server dependency: version coupling, protocol compatibility, backward compatibility, authentication.
Client Application | Application factors: version jump, install complexity, data migration, prerequisites.
Deployment Target | Target environment: VDI vs physical, hardware compatibility (assessment only), OS, VDI images.
Deployment | Rollout mechanics: deployment method, waves, user downtime, self-service options.
Licensing | License factors: model changes, count, license server impact.
Testing | Validation: test environment, functional testing, server integration, UAT.
Change Mgmt | Process overhead: approvals, user communication, help desk prep, stakeholders.
Risk | Business factors: rollback capability, criticality, timeline pressure.
KEY NOTES
1. Hardware Compatibility is ASSESSMENT ONLY - if upgrades needed, that's a separate project.
2. VDI Image Management = 1 (N/A) for physical-only deployments.
3. Deployment Target Complexity captures both VDI and physical diversity.
4. Server upgrade must typically happen BEFORE client upgrade when tight version coupling exists.
5. MES/Shop Floor clients often have stricter downtime constraints due to production impact.
HOW TO USE
1. Go to Estimation Matrix tab
2. Review Project Type Presets for similar project starting points
3. For each attribute, read Low/Medium/High descriptions
4. Enter complexity rating (1-5) in yellow Selection column
5. Set VDI Image Management = 1 if physical-only deployment
6. Review calculated Effort Hours
7. Adjust Contingency % based on project risk (default 15%)
8. Use Effort Breakdown tab to distribute hours across phases